## Product Catalog
Project Name | LockedMe.com
StakeHolders/Customers/Users | Company Lockers Pvt.Ltd.
Created By | Siddhant Nalawade
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
To develop prototype of an application which has Generic features and performs Business level operations to deliver as a high-end quality product. (LockedMe.com_Epic_001) | US001 | Display the Application name and developer details. | As a first time user Application name and the developer details be displayed on the welcome screen. | New
| US002 | Retrieving the file names in an ascending order. | On selecting it will return all the current file names in ascending order present in the selected directory. | New
| US003 | Add, Delete and Search a file from the existing directory. | On selecting it will Add, Delete or Search the user specified file in a specified directory. | New
| US004 | Navigate back to the main context. | On selecting the application will navigate back to the main content. This will allow to choose any other operations. | New
| US005 | Close the application. | On selecting this option by the user the application will get close. | New

## Sprint Planning
Project Name | LockedMe.com
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Siddhant Nalawade
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
To develop prototype of an application which has Generic features and performs Business level operations to deliver as a high-end quality product. (LockedMe.com_Epic_001) | US001 | Display the Application name and developer details. | As a first time user Application name and the developer details be displayed on the welcome screen. | 8 | 1
| US002 | Retrieving the file names in an ascending order. | On selecting it will return all the current file names in ascending order present in the selected directory. | 3 | 1
| US003 | Add, Delete and Search a file from the existing directory. | On selecting it will Add, Delete or Search the user specified file in a specified directory. | 5 | 2
| US004 | Navigate back to the main context. | On selecting the application will navigate back to the main content. This will allow to choose any other operations. | 5 | 2
| US005 | Close the application. | On selecting this option by the user the application will get close. | 8 | 2